HydroLoop

GJU Water & Energy Intelligence Program

IEEE Region 8 Sustainable Universities Program (2026)

Institution: German Jordanian University (GJU), Madaba, Jordan
Duration: 3 Months
Funding Requested: $1,400 USD

1. Executive Summary

HydroLoop is a smart sustainability platform designed to transform water and energy usage at GJU into a measurable, data-driven system.

At the center of the university lies a decorative water wheel that consumes electricity and loses water through evaporation without any monitoring. HydroLoop introduces a non-invasive IoT and AI-based system to measure these hidden costs and convert insights into actionable improvements.

The project delivers:

- Real-time measurement of water and energy consumption

- AI-driven analysis and optimization

- A campus-wide water monitoring system

- A data-backed sustainability improvement proposal

The result is a scalable solution that turns an unmonitored system into a flagship sustainability showcase.

2. Problem Statement

2.1 National Context

- Jordan is the world's second most water-stressed country (World Resources Institute, 2023)

- High dependency on imported energy

- Lack of granular monitoring leads to hidden inefficiencies

2.2 GJU-Specific Challenge

- Central water wheel operates daily with:

  - Continuous electricity usage

  - Unmeasured water evaporation

  - Periodic refilling with potable water

- No monitoring or optimization exists

- System runs regardless of actual usage

2.3 Campus-Wide Gap

- No building-level water monitoring

- Leaks and inefficiencies go undetected

- Resource waste is only visible after damage occurs

3. Proposed Solution

HydroLoop consists of two main layers and one institutional output:

3.1 Layer 1 – Smart Water Wheel Monitoring

A non-invasive sensor system to track:

- Energy consumption (motor usage)

- Water loss (evaporation and refill cycles)

- Weather impact

- Human presence in the area

This creates a full understanding of:

- Cost vs. usage

- Waste vs. value

3.2 Layer 2 – Campus Water Intelligence Network

Expansion to multiple buildings with:

- Flow sensors at water entry points

- AI-based anomaly detection

- Centralized monitoring dashboard

This enables:

- Leak detection

- Usage optimization

- Real-time insights across campus

3.3 Institutional Deliverable

A formal report including:

- Measured costs (water and energy)

- Identified inefficiencies

- Recommended improvements such as:

  - Smart operation (only when needed)

  - Evaporation reduction

  - Energy optimization

  - Alternative water sources

3.4 Public Engagement Feature

- QR code linked to live dashboard

- Students can view real-time data

- Turns infrastructure into an educational tool

4. Technical Architecture

System Components

Field Layer:

- Water wheel sensors

- Building flow sensors

- Weather station

- Camera for occupancy tracking

Key hardware: ESP32 microcontrollers, PZEM-004T clamp-on current/voltage sensors, JSN-SR04T waterproof ultrasonic water-level sensors, BME280 weather sensors, and ESP32-CAM modules for occupancy detection.

Data Layer:

- MQTT communication

- Time-series database

Processing Layer:

- AI models for prediction and anomaly detection

Visualization Layer:

- Dashboard (Grafana)

- Public display interface

5. Implementation Plan

Phase 1 – Setup (Week 1)

- Stakeholder alignment

- Procurement

Phase 2 – Wheel Monitoring (Weeks 2–3)

- Sensor installation

- Data streaming setup

Phase 3 – Network Deployment (Weeks 3–7)

- Install building sensors

- Validate data collection

Phase 4 – AI & Dashboard (Weeks 6–10)

- Model training

- Dashboard development

Phase 5 – Analysis (Weeks 10–11)

- Data evaluation

- Report preparation

Phase 6 – Final Launch (Week 12)

- Public dashboard release

- Final submission

6. Budget Summary

Total Estimated Cost: $1,400 USD

| Item | Qty | Unit Cost (USD) | Total (USD) |
| --- | --- | --- | --- |
| PZEM-004T current/voltage sensor (wheel motor) | 1 | $40 | $40 |
| JSN-SR04T waterproof ultrasonic sensor + mount | 1 | $30 | $30 |
| BME280 weather sensor + pole mount + wiring | 1 | $25 | $25 |
| ESP32-CAM + outdoor weatherproof enclosure | 1 | $25 | $25 |
| Weatherproof enclosures, cabling, hardware | — | $100 | $100 |
| Flow sensor + ESP32 + enclosure (x6 buildings) | 6 | $80 | $480 |
| LoRa gateway / central WiFi access point | 1 | $80 | $80 |
| Cloud VPS + domain (3 months) | 1 | $80 | $80 |
| Public kiosk tablet + weatherproof mount | 1 | $200 | $200 |
| Launch signage, QR plaques, infographics | — | $80 | $80 |
| Contingency (shipping, customs, spare parts) | — | $260 | $260 |
| TOTAL |  |  | ~$1,400 |

7. Key Performance Indicators (KPIs)

- Measured energy consumption of water wheel

- Measured water loss

- Identified reduction opportunities:

  - ≥30% energy savings

  - ≥40% water savings

- Minimum 6 monitored buildings

- Real-time dashboard availability

- Leak/anomaly detection events

- Public engagement via QR dashboard

8. Sustainability Impact

Environmental

- Reduced water waste

- Reduced energy consumption

- Lower carbon footprint

Institutional

- Long-term monitoring capability

- Data-driven decision making

Educational

- Real-time learning platform for students

- Increased awareness of sustainability

9. Scalability & Replication

HydroLoop is designed to be:

- Low-cost

- Easy to deploy

- Fully scalable

The system can be adapted to:

- Other universities

- Different infrastructure (fountains, labs, HVAC systems)

All components are based on:

- Open-source software

- Widely available hardware

## 10. Risk Assessment & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Admin restricts sensor access near wheel | Medium | High | Non-invasive design requires zero wheel modification; sensors mount on public poles/lampposts; MoU signed in Week 1 before procurement |
| Hardware import delays / customs in Jordan | Medium | Medium | $260 contingency included; parallel sourcing from regional and international suppliers; early procurement in Week 1 |
| Sensor measurements inaccurate / not trusted | Low | High | Dual-method validation: ultrasonic level drop + refill-event counting; cross-checked against manual flow measurements |
| Wi-Fi dead zones between campus buildings | Medium | Low | LoRa fallback included in budget; flexible mesh topology allows re-routing |
| ML model insufficient with limited training data | Low | Medium | Classical baselines (Isolation Forest, regression) chosen — effective with weeks of data; deep learning left for future phases |